## Sheet1
Sr. No. | Modules | Requirements | Assigned to | Priority | Closure date
1 | Dashboard - Time sheet statastics | Display Count of all the statstics below Pie chart | Garima | High | 2018-08-02
2 | Consultants list | Add Coulmn for Email sent and Email Date in Consultant List | Garima and Shani | High | 2018-08-02
3 | Client - Piechart | Add Procedure in Pie chart Correct procedure according to Pie chart | Garima and Shani | High | 2018-08-02
4 | Email | No email should be sent on Back No Email should be sent when user clicks on Close | Garima | High | 2018-08-02
5 | UI Changes | 1. Timesheet name should be same in all the pages 2. Email body Alignment 3. Email Popup should be aligned in the Middle 4. Piechart Resolution should be responsive | Krushita | High | 2018-08-02
6 | Client - Consultant list-Consultant History | Display the History of all the Emails sent to Consultant with Date | Garima and Shani | Medium | 2018-08-03
7 | Client - Email popup | Missing TS details against candidate | Shani and Shreya | High | 2018-08-03
8 | Mail Templaye - Subject line | Add Reminder count in the subject if Same email is sent for more than once - Need to check fisibility Also add subject as per the Template selected | Garima | Medium | 2018-08-03
9 | Client - Dropdown | Data filteration as per Year and Month selection(Grid and Pie chart) | Garima and Shani | High | 2018-08-03
10 | Client - Dropdown - LOB | 1. Correct value of LOB should be displayed after user clicks on Submit button 2. Also All the available LOB should be displayed even after user clicks on Submit button | Garima | High | 2018-08-03
11 | LIVE DB connection | For data verification live db data should be connected | Bharat and Anas | High | 2018-08-03